## Sheet1
Week | Component | Difficulty
2022-07-13 | Create spreadsheet of project plan | Easy
| Create trello board | Easy
| Create Git repo | Easy
2022-07-14 | Replace the scaffolding code with the flask code | Easy
| Run app localy | Medium
| Run app on azure | Medium
2021-01-15 | Set up GitHub Actions | Medium
| Create Github Actions Badge | Easy
| Create the App Service in Azure | Easy
| Test the app running in Azure App Service | Medium
2021-01-18 | Set up the Azure DevOps pipeline | Medium
2021-01-19 | Create architecture overview | Easy
| Take screenshots demonstrating key steps | Easy
| Create README file with instructions | Easy
| Create demo video | Easy
Goals
Submit project
Q4 plan | Submit the project
Yearly plan | Check that the app is still working